## Tabelle1
Master Thesis on Vision guided 6-axis Robotic Arm for Material Inspection on a Conveyor Line
Months/Work Details | March | April |  |  |  | May |  |  |  | June |  |  |  | July
| Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
1. Objective Scope and Definition 2. Research and Literature Review | bar: March Week 4
3. Hardware and Software Selection and Installation | bar: April Week 1
4. Integration of UR3E Robot and 3D Vision Camera & Gripper | bar: April Week 1 to April Week 3
5. Conceptual and Detailed design of a mini conveyor line. | bar: April Week 3
6. Material Selection and Assemblyof the conveyor. | bar: April Week 3 to April Week 4
7. Integration of Conveyor Line with the Robot Test bench | bar: May Week 1 to May Week 2
8. Algorithm Development and Simulation | bar: May Week 1 to June Week 1
9. Testing and Validation | bar: June Week 2 to June Week 4
10. Documentation and Iterative Improvement | bar: July Week 1 to July Week 3
11. Presentation and Defense | bar: July Week 4
Start Date: 20th March, 2024 | April Week 1: Work Completed
End Date: 31st July, 2024 | April Week 1: Work Remaining
Student: Bibek Gupta (EU4M)
Supervisors: 1. Prof. Juan Carlos ÁLVAREZ ÁLVAREZ 2. Prof. Miguel Ángel JOSÉ PRIETO